Dissertation Planning Worksheet

Study Development Worksheet

## Example

My ideal deadline: 20th May (Real Deadline 30th May)

Tips: Be specific about tasks and time; Allow extra ‘buffer time’; don’t forget to allow for sleep/eating/commuting/work/socialising etc!

| TASK | Identify Resources | Research | Plan | Get writing! | Edit | Extra research | Complete final draft | Edit and proofread |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Timeframe/ deadline | - 24th Jan 9-6 - 30th Jan 9-6 - Trip to library 31st Jan 9-6 | Every Tues, Thurs and Sat in Feb 10-6 | 3rd March 10-2 and 7 onwards | Every Tues, Thurs and Sat in March & April 10-6 | 1st May 9-11, 3rd May 9-5, 4th & 5th May after 7pm | 7th May 2-6pm 8th May 9-5 | 10th, 11th May afternoons, all day 12th May | 16th-17th May afternoons |
| Details | - Create a reading list. - Skim abstracts/ indexes/ chapter headings/ starts of paragraphs to identify relevant literature. - Where are the resources? Make sure you can access them! - Do you need to organise practical research? When? Where? Who? | - Read and take detailed notes. - Highlight key ideas. - Reference as you go. - Note page numbers. - Write memos for your future self! - Link connected ideas. - Use colour coding? - Use diagrams? | - Draft the structure. - Divide into chapters/ sections/ sub-headings/ paragraph topics. - Note which research feeds into which section. - Bullet point key ideas in each section. | - Aim to work on specific, short sections one at a time. - Turn bullet points and paragraph topics into full sentences. | - Do you need to alter the structure? - Is everything relevant? - Are sentences short, clear and flowing? - Does each paragraph have a clear topic? | Tie up any missing research; missing references; fact checking. | Make sure all chapters, sections, paragraphs and sentences are complete, and references done. | - Are all points -relevant to the title? - Are sentences short, clear and flowing? - Does each paragraph have a clear topic? - Are all ideas and quotations referenced? - Make sure you are within 10% of your word count. - Ask friends and family to look at your work. |

## Worksheet

| TASK | Identify Resources | Research | Plan | Get writing! | Edit | Extra research | Complete final draft | Edit and proofread |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Timeframe/ deadline |  |  |  |  |  |  |  |  |
| Details |  |  |  |  |  |  |  |  |

Support: Study Development offers workshops, short courses, 1 to 1 and small group tutorials.

- Book a tutorial or join a workshop on the Study Development tutorial and workshop webpage or search ‘YSJ study development tutorials.’

- Access our Study Success resources on the Study Success webpage or search ‘YSJ study success.’